3rd Heads of Schools and Administrative Units Meeting

Monday, 17 February 2020

Deliberated and Resolved Points for Action by Staff / Unit Concerned :-

01 Speakers in the campus. It was directed to fit speakers on campus in such a way that minimum digging/without digging, it can be fitted. To create group email id's of the students. (K. Shah)

02(i)Certificate Course for music/band to be started and purchasing of band equipment. 18% GST to be charged for programme/course for students outside RSU.          (ii) Football ground to be constructed. It was stated that the quotations will be obtained within 10 days.  (G. Kushwah)

03 Increase in electric capacity/purchasing of generator before March-April. It was suggested to carry out video conference with UGVCL officers to save time. (A. Mishra)

04  (i)To explore possibilities for installation of water cooler near parade ground for the students. (ii) To expedite new road from Sampa village to Main gate of RSU. (iii) Also to expedite development of Dahegam Circle (V. Gole)

05  A marathon is organized by RSU from Gandhinagar to RSU, Lavad, on or about 27th or 28th March, 2020.It was stated that SP, Gandhinagar, Collector (Gandhinagar) and Gandhinagar Municipal Corporation have been contacted. For critical medical emergency, the medical agencies/NGOs will be contacted. Sponsorship/partnership from GFSU & GNLU will be sought. (K V Ravi Kumar)

06  (i) Canteen facilities in RSU campus. New caterers will be handed over the charge of the canteen shortly. (ii) To meet Designers & Printers who are carrying out the work of printing for GNLU to print new letterhead of DG Sir.(iii) To prepare a unique ID for every employee. (P. Soni)

07  (i) To visit FRC for B.Tech & M.Tech Courses. (ii) To start Post Graduate Diploma in Defense Communication and Technology next year. (iii) Cybercrime Training programme has been postponed to 12th March, 2020. (C. Parekh)

08 (i) Faulty profiles will be linked with website of RSU. (ii) To contact Mr. Bhalla, Director, MHA, for getting proposal for Chatbot.(R.Sheth)

09(i) To follow up for setting up Traffic Management Institute in RSU in consultation with STB. (ii) To follow up on preparation of Disaster Mitigation Plan for RSU in consultation with GIDM. (iii)To follow up on MOU with Prayas, School of Internal Security & Police Administration. (iv) Email accounts have been changed for a number of faculty members. It was discussed that a uniform policy may be adopted in this regard. Shri Ravi Sheth and Shri Keyur Shah to discuss with DG Sir. (A. Mehta)

10 (i) To explore possibility for installation of ATM in the premises of RSU either in shop or near gate No. 2 to be installed by either Corporation Bank of HDFC Bank, first come first basis. (ii) To digitize payment above Rs. 1.00 lacs (iii) To work out on the implementation of 7th pay commission to permanent teaching staff of the RSU. (iv) To work out about the recruitments made by the  RSU without approval of the Government. A Committee is formed consisting of Shri Sumit Choudhary, Shri Sushil Goswami and Shri Kundan Parmar to work out on the above issue. (K. Parmar)

11 List of vendors to be obtained from the Deans regarding empanelment of book sellers. (ii) Presentation of Library Space Requirement to be made before the Committee headed by Dir (ISSM). (P. Parekh)

12  To start integrated LL.B programme i.e. B.Sc LLB & BA LL.B programmes. Approval has to be obtained from the Bar Council of India for these programmes. To start one year LL.M programme which is under process. (A. Tripathi).

13 (i) Malhaar is scheduled from 13-17th March, 2020 at RSU. It was suggested to establish students’ activity club should be established. (ii) Recruitment of one Asst. Prof. (Criminology) is needed to share the workload. (iii) Certificate course on “Fire Safety & Security” to be finalized. (iv) Restructuring of CDF. National & International members to be invited in CDF.  (Divyashree)

14 To follow up about the status of National Police University. (S. Choudhary)

15 Shri Vijay Vaghela, OSD to DG is expected to share the contact details of expert of disaster management with Dr. Akshat Mehta and Dr. Sumit Kumar Choudhary. (V. Vaghela)